## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
I catch CoViD | 5 | 40 | 200 | 2021-01-14 | Mitigated | M | learned instructor has extension possible
My gecko is not working | 3 | 20 | 60 | 2021-01-14 |  | O | Test it. If mine not working, contact instructor
Develop physics task with proper project setup | 20 | 40 | 800 | 2023-03-19 | Resolved | R | Unit tested tasks and inputs to ensure working order
Develop cart physics | 40 | 40 | 1600 | 2023-03-22 | Resolved | O | Focus on just making the cart work first
Develop cannon | 40 | 40 | 1600 | 2023-03-22 | Resolved | O | Focus on just making the cannon work on its own
Develope bombs throwing off canyon | 40 | 20 | 800 | 2023-03-22 | Resolved | O | Focus on just making the bobs work on its own
Can't combine all three physics aspects | 40 | 70 | 2800 | 2023-03-22 | Resolved | O | Should not be an issue if proper unit tests take place
Struggle to create winning condition | 20 | 20 | 400 | 2023-03-22 | Owned | O | Will be last issue to resolve in the game
Spill water on my gecko board while working | 5 | 70 | 350 | 2023-03-22 | Accepted | A | I will be proactive about keeping my board dry

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100